## Sheet1
Sprint Project
No | Job Description | Penanggung Jawab | Target Selesai | Tanggal Selesai | Status
1 | Load Data | Fira | 2021-10-19 | 2021-10-25 | Done
2 | Preprocessing | Fira | 2021-10-26 | 2021-10-25 | Done
3 | Data Augmentation 1 & Normalization | Fira | 2021-11-01 | 2021-10-25 | Done
4 | Modelling (1st Scenario) | Fitri | 2021-11-06 | 2021-10-27 | Done
5 | Modelling (2nd Scenario) | Fitri | 2021-11-13 | 2021-10-27 | Done
6 | Plotting & Saving Models (Batch 1) | Fitri | 2021-11-20 | 2021-10-27 | Done
7 | Splitting Data | Fira | 2021-11-20 | 2021-11-09 | Done
8 | Modelling (3rd Scenario) | Fira | 2021-11-20 | 2021-11-09 | Done
9 | Modelling (4th Scenario) | Fira | 2021-11-20 | 2021-11-09 | Done
10 | Modelling (5th Scenario) | Fitri | 2021-11-20 |  | Waiting
11 | Plotting & Saving Models (Batch 2) | Fitri | 2021-11-21 |  | Waiting